## REQUIREMENTS
| FEATURES | SUB-FEATURES | V1.0 | V2.0 | V3.0
COUNT |  |  | 53 | 39 | 14
FRONTEND | Develop business-portal |  | √
| Develop visplayer-framework |  | √
| Develop users-manager |  | √
| Develop files-manager |  | √
| Develop scene-manager |  | √
| Develop tools-manager |  | √
| Develop process-manager |  |  | √
| Develop display-manager |  | √
BACKEND | Develop version-manager |  | √
| Develop synchronization-manager |  | √
| Develop geometry-descriptor |  | √
| Develop geometry-importers | Develop geometry-importer (PCD) | √
|  | Develop geometry-importer (PLY) | √
|  | Develop geometry-importer (OBJ) | √
|  | Develop geometry-importer (STL) | √
|  | Develop geometry-importer (...) |  |  | √
| Develop geometry-exporters | Develop geometry-exporter (PLY) | √
|  | Develop geometry-exporter (OBJ) | √
|  | Develop geometry-exporter(STL) | √
|  | Develop geometry-exporter (VIS) | √
|  | Develop geometry-exporter (...) |  |  | √
| Develop geometry-positioner |  | √
| Develop geometry-orientor |  | √
| Develop geometry-reconstructors | Develop geometry-reconstructor (RBF) | √
|  | Develop geometry-reconstructor (Diffusion) | √
|  | Develop geometry-reconstructor (Poisson) |  | √
|  | Develop geometry-reconstructor (Level Set) |  | √
|  | Develop geometry-reconstructor (...) |  |  | √
| Develop geometry-polygonizers | Develop geometry-polygonizer (Cell Based) | √
|  | Develop geometry-polygonizer (Marching Cubes) | √
|  | Develop geometry-polygonizer (Dual Contouring) |  | √
|  | Develop geometry-polygonizer (...) |  |  | √
| Develop mesh-registrators | Develop mesh-registrator (ICP) | √
|  | Develop mesh-registrator (...) |  |  | √
| Develop mesh-analyzers | Develop mesh-analyzer (Density) | √
|  | Develop mesh-analyzer (Normal) | √
|  | Develop mesh-analyzer (Gradient) | √
|  | Develop mesh-analyzer (Laplacian) | √
|  | Develop mesh-analyzer (Curvatures) | √
|  | Develop mesh-analyzer (...) |  |  | √
| Develop mesh-healers | Develop mesh-healer (Normal Orientation) |  | √
|  | Develop mesh-healer (Surface Based) | √
|  | Develop mesh-healer (Volume Based) | √
|  | Develop mesh-healer (...) |  |  | √
| Develop mesh-remeshers | Develop mesh-remesher (Delaunay) | √
|  | Develop mesh-remesher (Greedy) | √
|  | Develop mesh-remesher (Variational) |  | √
|  | Develop mesh-remesher (Incremental) |  | √
|  | Develop mesh-remesher (Curvature Flow) | √
|  | Develop mesh-remesher (...) |  |  | √
| Develop mesh-simplifiers | Develop mesh-simplifier (Vertex Clustering) | √
|  | Develop mesh-simplifier (Incremental) |  | √
|  | Develop mesh-simplifier (Shape Approximation) |  | √
|  | Develop mesh-simplifier (...) |  |  | √
| Develop mesh-smoothers | Develop mesh-smoother (Laplacian) | √
|  | Develop mesh-smoother (Manifold Harmonics) | √
|  | Develop mesh-smoother (Diffusion Flow) | √
|  | Develop mesh-smoother (Curvature Flow) | √
|  | Develop mesh-smoother (Spectral) |  | √
|  | Develop mesh-smoother (Variational) |  | √
|  | Develop mesh-smoother (...) |  |  | √
| Develop mesh-deformers | Develop mesh-deformer (Shell) | √
|  | Develop mesh-deformer (Multiscale) | √
|  | Develop mesh-deformer (Gradient Based) | √
|  | Develop mesh-deformer (Laplacian Based) | √
|  | Develop mesh-deformer (Local Transformation) | √
|  | Develop mesh-deformer (Lattice Based) | √
|  | Develop mesh-deformer (Cage Based) | √
|  | Develop mesh-deformer (RBF) | √
|  | Develop mesh-deformer (...) |  |  | √
| Develop mesh-transformers | Develop mesh-transformer (Voronoi) | √
|  | Develop mesh-transformer (Hallow) | √
|  | Develop mesh-transformer (Offset) | √
|  | Develop mesh-transformer (Laminate) | √
|  | Develop mesh-transformer (Slicing) | √
|  | Develop mesh-transformer (...) |  |  | √
| Develop mesh-comparitor |  |  | √
| Develop mesh-finder |  |  | √
| Develop ai-engine |  |  | √
| Develop graphics-shaders | Develop graphics-shader (Discarding) |  | √
|  | Develop graphics-shader (Phong) |  | √
|  | Develop graphics-shader (Analytical) |  | √
|  | Develop graphics-shader (Anisotropic) |  | √
|  | Develop graphics-shader (Data Driven) |  | √
|  | Develop graphics-shader (Shrinking) |  | √
|  | Develop graphics-shader (Sihlouetting) |  | √
|  | Develop graphics-shader (Contouring) |  | √
|  | Develop graphics-shader (Subdivision) |  | √
|  | Develop graphics-shader (Point Clouds) |  | √
|  | Develop graphics-shader (Cutting Plane) |  | √
|  | Develop graphics-shader (Volume Probe) |  | √
|  | Develop graphics-shader (Flow) |  | √
|  | Develop graphics-shader (Hedge) |  | √
|  | Develop graphics-shader (Morphing) |  | √
|  | Develop graphics-shader (Explosion) |  | √
|  | Develop graphics-shader (...) |  |  | √
| Develop graphics-painter |  |  | √
| Develop graphics-filter | Develop graphics-filter (Brightness) |  | √
|  | Develop graphics-filter (Contrast) |  | √
|  | Develop graphics-filter (Saturation) |  | √
|  | Develop graphics-filter (Gamma) |  | √
|  | Develop graphics-filter (Sharpering) |  | √
|  | Develop graphics-filter (Bluring) |  | √
|  | Develop graphics-filter (Levels) |  | √
|  | Develop graphics-filter (...) |  |  | √
| Develop process-automator |  |  | √
Note on D1: DONG: Architecture Fundamental Geometry Processors
Note on E1: DONG: Geometry Processor Extensions Process Management Geometry Search Basic Graphics Processors
Note on F1: DONG: Geometry Processor Extensions Graphics Processor Extensions

## SCHEDULE
VERSION | LEN. | STA. | 2017 |  | 2018 | [11 empty] | 2019 | [11 empty] | 2020
|  |  | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
MILESTONES
V1.0 | 18 | D | bar: 2017 11 to 2018 8
α | bar: 2018 9 to 2018 12
β | bar: 2019 1 to 2019 4
R
V2.0 | 12 | D | bar: 2019 5 to 2019 10
α | bar: 2019 11 to 2020 1
β | bar: 2020 2 to 2020 4
R
V3.0 | 6 | D | bar: 2020 5 to 2020 6
α | bar: 2020 7 to 2020 8
β | bar: 2020 9 to 2020 10
R
RES. | NUM.
Full stack developer | 2 | bar: 2018 2; 2019 5
Algorithm developer | 2 | bar: 2018 5; 2019 5
Graphics developer | 1 | bar: 2019 8
Integration developer | 1 | bar: 2018 9
Testing developer | 1 | bar: 2019 11
Note on F3: Dong Zhao: Milestone #1
Note on M3: Dong Zhao: Milestone #2
Note on Q3: Dong Zhao: Milestone #3
Note on U3: Dong Zhao: Milestone #4
Note on AA3: Dong Zhao: Milestone #5
Note on AD3: Dong Zhao: Milestone #6
Note on AG3: Dong Zhao: Milestone #7